## Sheet1
CONTAINER MANAGEMENT SYSTEM
Scrum Master | Harshwardhan Mehrotra
Project Start Date | 2/16/2022
Project End Date | 2022-05-31
Project Id | Group No. 4
Project Description | Container Mangement System
Team Members | Name |  | Role
| Harshwardhan Mehrotra |  | Project Developer
| Shreyansh Dubey |  | Project Developer
| Soham Dhande |  | Project Developer
| Viren Ghuikhedkar |  | Project Developer
| Prof. Nilesh Marathe |  | Project Guide
Task Name | Sub Tasks | Task Status | Priority | Assigned To | Assigned Date | Deadline | Start Date | End Date | % Done
[10 empty] | STATUS KEY | PRIORITY KEY
Studying the Research Paper | Abstract | Complete | High | Viren And Soham | 2/16/2022 | 2/18/2022 | 2021-03-18 | 2021-03-25 | 100% | Not Started | High
| Introduction | Complete | High | Viren And Soham | 2/18/2022 | 2/23/2022 | 20/18/2021 | 2021-03-25 | 100% | In Progress | Medium
| Related Works | Complete | High | Viren And Soham | 2/25/2022 | 2022-02-03 | 2021-05-20 | 2022-05-25 | 100% | Complete | Low
| Revision | Complete | Low | Viren And Soham | 2022-02-03 | 2022-04-03 | 2021-05-25 | 2022-05-30 | 100%
Start with Backend | Start with learning about docker api | Complete | High | Harshwardhan | 2022-09-03 | 2022-11-03 | 2022-09-03 | 2022-03-05 | 100% | 50%
| create containers | Complete | High | Harshwardhan | 2022-04-12 | 2022-05-02 | 2022-04-12 | 2022-04-13 | 100%
| list containers | Complete | High | Harshwardhan | 2022-04-16 | 2022-05-02 | 2022-04-16 | 2022-04-16 | 100%
| list images | Complete | High | Harshwardhan | 2022-04-17 | 2022-05-02 | 2022-04-17 | 2022-04-17 | 100%
| List Networks | Complete | High | Harshwardhan | 2022-04-18 | 2022-05-02 | 2022-04-18 | 2022-04-20 | 100%
| Get container Details | Complete | High | Harshwardhan | 2022-04-22 | 2022-05-02 | 2022-04-22 | 2022-04-24 | 100%
Start With Frontend | start working on the design | Complete | High | Shreyansh | 2022-04-12 | 2022-05-02 | 2022-04-12 | 2022-04-13 | 100%
| Create page for Images | Complete | High | Shreyansh | 2022-04-16 | 2022-05-02 | 2022-04-16 | 2022-04-16 | 100%
| Create page for Volumes | Complete | High | Shreyansh | 2022-04-17 | 2022-05-02 | 2022-04-17 | 2022-04-17 | 100%
| Create page for Container info | Complete | High | Shreyansh | 2022-04-18 | 2022-05-02 | 2022-04-18 | 2022-04-20 | 100%
| Create Page for Network Info | Complete | High | Shreyansh | 2022-04-22 | 2022-05-02 | 2022-04-22 | 2022-04-24 | 100%
Total Hours Sent | 50
Project Progress | 100